## Backlog
Task ID | Title | Description | Owner | Priority | Status | Sprint | Start Date | End Date | Comments
T-001 | Frontend scaffold (Vite + React) | Create Vite project, React Router, initial pages | Preeti | High | Done | Sprint 1 | 2025-12-10 | 2025-12-15
T-002 | Search API integration | Integrate /search endpoint, filters and results | Preeti | High | Done | Sprint 1 | 2025-12-16 | 2025-12-20
T-003 | Flight Details & Price Polling | Show flight details and poll dynamic price endpoint | Preeti | High | In Progress | Sprint 2 | 2025-12-21 | 2026-01-05 | Polling every 10s
T-004 | Seat selector UI | Interactive seat map with class-based pricing | Preeti | Medium | To Do | Sprint 3 |  |  | Requires seat metadata from backend
T-005 | Booking hold & confirm | Implement hold (initiate) and confirm endpoints in frontend flow | Preeti | High | Done | Sprint 2 | 2026-01-03 | 2026-01-06 | Uses sessionStorage to persist hold id
T-006 | Passenger multi-entry & validation | Allow 1-9 passengers; inline validation for email/name | Preeti | High | Done | Sprint 3 | 2026-01-06 | 2026-01-08 | Client-side validation implemented
T-007 | Auth: Register/Login | Add register and login pages, session restore via /me | Preeti | High | Done | Sprint 2 | 2025-12-25 | 2026-01-02 | Credentials: cookies included
T-008 | Booking history & receipts | List user bookings and allow JSON/PDF download | Preeti | Medium | Done | Sprint 3 | 2026-01-07 | 2026-01-08 | PDF endpoint: /bookings/<pnr>/receipt?format=pdf
T-009 | Tailwind styling and responsive layout | Integrate Tailwind via PostCSS and apply base styles | Preeti | Medium | Done | Sprint 1 | 2025-12-14 | 2025-12-20 | Imported tailwind.css in main.jsx
T-010 | Tests & Docs | Add README, setup guide, unit test plan and presentation | Preeti | Medium | In Progress | Sprint 4 | 2026-01-08 |  | Generate docs under docs/
T-011 | Concurrency hardening | Ensure seat holds expire and confirm is transactional | Preeti | High | To Do | Sprint 4 |  |  | Backend DB transactional logic
T-012 | CI / Deployment | Add GitHub Actions workflow for tests and deploy | Preeti | Low | To Do | Sprint 5 |  |  | Optional