## Defects
Defect ID | Summary | Steps to Reproduce | Severity | Priority | Status | Assigned To | Reported By | Date Found | Environment | Resolution
D-001 | Login returns 500 on invalid payload | 1. POST /login with missing fields\n2. Observe server 500 | Major | High | Open | Backend Team | QA | 2026-01-03 | Local | Investigate payload handling and input validation
D-002 | Seat hold not released on timeout | 1. Initiate hold\n2. Do not confirm\n3. Seats stay reserved | Critical | High | Open | Backend Team | QA | 2026-01-04 | Local | Expiry job not firing
D-003 | Price polling causes UI jitter | 1. Open flight details\n2. Observe layout shift when price updates | Minor | Low | Open | Frontend Team | QA | 2026-01-06 | Chrome | Stabilize layout and animate price changes
D-004 | Register allows duplicate email | 1. Register with existing email\n2. Account created/exception | Major | High | Open | Backend Team | QA | 2026-01-07 | Local | Add unique constraint and error handling